## BMS MoM
| Project -Battery Management System for Electric Vehical |  |  | Date | 2021-10-09
| Minutes of the Meeting |  |  | Time | 22:00
|  |  |  | Week | 40
Contract No | M_JUL_21_P1_BMS |  |  | Team Name | Matlab Riders
Project Name | Battery Management System for Electric Vehical |  |  | Project Manager | Mr. Rohan Doshi Sir
Project Address | Pune |  |  | Scrum Master | Diptee Joshi
Commencement Date |  |  |  | Project Owner | Omkar Gosavi
Closure date |  |  |  | Team Members | Bhagyesh Bhosale
Allocation Date |  |  |  |  | Jayesh Kothawde
Sudhir Mane
Vinit Bijagare
Bhushan Kanure
PROJECTS REQUIREMENTS
Points Discussed | Remarks | Action | Target Date | Actual Date | Responsible
Requirements Gatherings | Details discussion is done on Scope, reqirments gatherings of Projects- To decide Project scope like Monitoring of various battery parameters such as SOC, SOH, V, I, Battery temp, Load, battery output estimation as per load variation according to usages of Light, AC, Music System, etc.
Additional Requirents | Over Temp Protection, Various I/O, | each members to search various I/O for their requirements
SOC-inputs, charges avl, estimation, estimation calculation after 5KM or perticaular time, charging and discharging time,
Health- count of cycle,time for each cycle
active cell balancing to consider
Documentation | Presentation done to Rohan sir by all the team menbers | each members to search various I/O for their requirements, data types, min/max values, of each parameters | 2021-10-10 |  | All team
| Project -Battery Management System for Electric Vehical |  |  | Date | 2021-10-07
| Minutes of the Meeting |  |  | Time | 7:00
|  |  |  | Week | 40
Contract No | M_JUL_21_P1_BMS |  |  | Team Name | Matlab Riders
Project Name | Battery Management System for Electric Vehical |  |  | Project Manager | Mr. Rohan Doshi Sir
Project Address | Pune |  |  | Scrum Master | Diptee Joshi
Commencement Date |  |  |  | Project Owner | Omkar Gosavi
Closure date |  |  |  | Team Members | Bhagyesh Bhosale
Allocation Date |  |  |  |  | Jayesh Kothawde
Sudhir Mane
Vinit Bijagare
Bhushan Kanure
PROJECTS REQUIREMENTS
Points Discussed | Remarks | Action | Target Date | Actual Date | Responsible
Requirements Gatherings | Details discussion is done on Scope, reqirments gatherings of Projects- To decide Project scope like Monitoring of various battery parameters such as SOC, SOH, V, I, Battery temp, Load, battery output estimation as per load variation according to usages of Light, AC, Music System, etc.
Additional Requirents | Over Temp Protection, Various I/O, | each members to search various I/O for their requirements
SOC-inputs, charges avl, estimation, estimation calculation after 5KM or perticaular time, charging and discharging time,
Health- count of cycle,time for each cycle
active cell balancing to consider
Documentation | To prepare details documentation, Presentation of project , Deadline etc | each members to prepare presentationfor their requirements | 2021-10-09
| Project -Battery Management System for Electric Vehical |  |  | Date | 2021-10-06
| Minutes of the Meeting |  |  | Time | 22:00
|  |  |  | Week | 40
Contract No | M_JUL_21_P1_BMS |  |  | Team Name | Matlab Riders
Project Name | Battery Management System for Electric Vehical |  |  | Project Manager | Mr. Rohan Doshi Sir
Project Address | Pune |  |  | Scrum Master | Diptee Joshi
Commencement Date |  |  |  | Project Owner | Omkar Gosavi
Closure date |  |  |  | Team Members | Bhagyesh Bhosale
Allocation Date |  |  |  |  | Jayesh Kothawde
Sudhir Mane
Vinit
Bhushan Kanure
PROJECTS REQUIREMENTS
Points Discussed | Remarks | Action | Target Date | Actual Date | Responsible
Requirements Gatherings | Details discussion is done on Scope, reqirments gatherings of Projects- To decide Project scope like Monitoring of various battery parameters such as SOC, SOH, V, I, Battery temp, Load, battery output estimation as per load variation according to usages of Light, AC, Music System, etc.
Requirements Allocation | Requirenents allocation to each team member and prepare documentation | Allocation done to each team members by Omkar sir
Documentation | To prepare details documentation, Presentation of project , Deadline etc
| Project -Battery Management System for Electric Vehical |  |  | Date | 2021-10-05
| Minutes of the Meeting |  |  | Time | 6:30PM
|  |  |  | Week | 40
Contract No | M_JUL_21_P1_BMS |  |  | Team Name | Matlab Riders
Project Name | Battery Management System for Electric Vehical |  |  | Project Manager | Mr. Rohan Doshi Sir
Project Address | Pune |  |  | Scrum Master | Diptee Joshi
Commencement Date |  |  |  | Project Owner | Omkar Gosavi
Closure date |  |  |  | Team Members | Bhagyesh Bhosale
Allocation Date |  |  |  |  | Jayesh Kothawde
Sudhir Mane
Vinit
Bhushan Kanure
PROJECTS REQUIREMENTS
Points Discussed | Remarks | Action | Target Date | Actual Date | Responsible
Requirements Gatherings | Details discussion is done on Scope, reqirments gatherings of Projects- To decide Project scope like Monitoring of various battery parameters such as SOC, SOH, V, I, Battery temp, Load, battery output estimation as per load variation according to usages of Light, AC, Music System, etc.
Additional Requirents | Over Temp Protection, Various I/O,
SOC-inputs, charges avl, estimation, estimation calculation after 5KM or time, charging and discharging time,
Health- count of cycle,time for each cycle
active cell balancing
Documentation | To prepare details documentation, Presentation of project , Deadline etc
| Project -Battery Management System for Electric Vehical |  |  | Date | 2021-10-03
| Minutes of the Meeting |  |  | Time | 6:30PM
|  |  |  | Week | 40
Contract No | M_JUL_21_P1_BMS |  |  | Team Name | Matlab Riders
Project Name | Battery Management System for Electric Vehical |  |  | Project Manager | Mr. Rohan Doshi Sir
Project Address | Pune |  |  | Scrum Master | Diptee Joshi
Commencement Date |  |  |  | Project Owner | Omkar Gosavi
Closure date |  |  |  | Team Members | Bhagyesh Bhosale
Allocation Date |  |  |  |  | Jayesh Kothawde
Sudhir Mane
Vinit
Bhushan Kanure
PROJECTS REQUIREMENTS
Points Discussed | Remarks | Action | Target Date | Actual Date | Responsible
Requirements Gatherings | Details discussion is done on Scope, reqirments gatherings of Projects- To decide Project scope like Monitoring of various battery parameters such as SOC, SOH, V, I, Battery temp, Load, battery output estimation as per load variation according to usages of Light, AC, Music System, etc.
Allocation of Work to Team Members | Rohan sir told us to devide the project scope to each team menbers
Documentation | To prepare details documentation, Presentation of project , Deadline etc